## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US001 | User Registration | As a new user, I want to register an account, so that I can access the system | High | 1 | 1. User can enter name, email, password 2. Email format validated 3. Password strength checked 4. Account created successfully | 3 | Phase 2 - Sprint 1 | 2025-04-15 | 2025-03-30
US002 | User Login | As a registered user, I want to log in, so that I can access my personalized dashboard | High | 1 | 1. User can enter email and password 2. Invalid credentials show error message 3. Session created on successful login | 2 | Phase 2 - Sprint 1 | 2025-04-15 | 2025-03-30
US003 | Role Selection | As a user, I want to select my role (TA or MO), so that I can access appropriate features | High | 1 | 1. User can select TA or MO role 2. Role stored in user profile 3. UI adapts to selected role | 1 | Phase 2 - Sprint 1 | 2025-04-15 | 2025-03-30
US004 | TA Profile Creation | As a TA applicant, I want to create my profile, so that MO can review my information | High | 1 | 1. TA can enter personal details (name, student ID, major, year) 2. TA can add contact information 3. Profile saved to system | 5 | Phase 2 - Sprint 1 | 2025-04-15 | 2025-03-30
US005 | Resume Upload | As a TA applicant, I want to upload my resume/CV, so that MO can review my qualifications | High | 1 | 1. TA can upload PDF/DOC resume 2. File size limit enforced (max 5MB) 3. Resume stored and linked to profile | 3 | Phase 2 - Sprint 1 | 2025-04-15 | 2025-03-30
US006 | Skills Declaration | As a TA applicant, I want to declare my skills, so that the system can match me with suitable jobs | Medium | 1 | 1. TA can select skills from predefined list 2. TA can add custom skills 3. Skills saved to profile | 2 | Phase 2 - Sprint 1 | 2025-04-15 | 2025-03-30
US007 | Job Posting Creation | As an MO, I want to create and publish a job posting, so that TAs can view and apply | High | 2 | 1. MO can enter job title and description 2. MO can specify required skills 3. MO can set deadline 4. Job posted and visible to TAs | 5 | Phase 2 - Sprint 2 | 2025-03-30 | 2025-04-12
US008 | Job Listing Display | As a TA, I want to view available job postings, so that I can find suitable positions | High | 2 | 1. All active jobs displayed 2. Jobs sorted by deadline 3. Job details visible on click | 3 | Phase 2 - Sprint 2 | 2025-03-30 | 2025-04-12
US009 | Job Search/Filter | As a TA, I want to search and filter jobs, so that I can find positions matching my skills | Medium | 2 | 1. TA can search by keyword 2. TA can filter by required skills 3. Filter results update in real-time | 3 | Phase 2 - Sprint 2 | 2025-03-30 | 2025-04-12
US010 | Job Application | As a TA, I want to apply for a job, so that I can be considered for the position | High | 2 | 1. TA can view job details before applying 2. TA can submit application 3. Application linked to TA profile 4. Confirmation shown after submission | 5 | Phase 2 - Sprint 2 | 2025-03-30 | 2025-04-12
US011 | Application Status View | As a TA, I want to view my application status, so that I can track my job applications | High | 2 | 1. TA can see all their applications 2. Status shown (Pending/Accepted/Rejected) 3. Status updates in real-time | 2 | Phase 2 - Sprint 2 | 2025-03-30 | 2025-04-12
US012 | Applicant List View | As an MO, I want to view all applicants for my job, so that I can evaluate them | High | 2 | 1. MO can see list of applicants 2. MO can view applicant profiles 3. MO can view resumes | 3 | Phase 2 - Sprint 2 | 2025-03-30 | 2025-04-12
US013 | Applicant Selection | As an MO, I want to select an applicant, so that I can offer them the TA position | High | 2 | 1. MO can accept or reject applicants 2. TA notified of decision 3. Application status updated | 3 | Phase 2 - Sprint 2 | 2025-03-30 | 2025-04-12
US014 | Logout | As a user, I want to log out, so that I can securely exit the system | Medium | 1 | 1. User can click logout 2. Session terminated 3. Redirected to login page | 1 | Phase 2 - Sprint 1 | 2025-04-15 | 2025-05-20
US015 | Profile Editing | As a TA, I want to edit my profile, so that I can keep my information up to date | Medium | 2 | 1. TA can modify profile details 2. Changes saved immediately 3. Resume can be updated | 2 | Phase 2 - Sprint 3 | 2025-04-15 | 2025-05-20
US016 | AI Skill Matching | As a TA, I want to receive AI-powered job recommendations, so that I can find the best matching positions | Medium | 3 | 1. System analyzes TA skills and job requirements 2. Match percentage displayed for each job 3. Top 5 recommended jobs shown | 8 | Phase 3 - Sprint 3 | 2025-04-18 | 2025-04-30
US017 | AI Missing Skills Detection | As a TA, I want to know which skills I lack for a job, so that I can improve my qualifications | Medium | 3 | 1. System identifies missing required skills 2. Suggestions for skill improvement provided 3. Learning resources recommended | 5 | Phase 3 - Sprint 3 | 2025-04-18 | 2025-04-30
US018 | Admin Workload Statistics | As an admin, I want to view workload statistics, so that I can monitor system usage | Low | 3 | 1. Number of active TAs displayed 2. Number of job postings shown 3. Application statistics available 4. Data exportable | 5 | Phase 3 - Sprint 3 | 2025-04-18 | 2025-04-30
US019 | Job Posting Management | As an MO, I want to manage my job postings, so that I can update or remove them | Medium | 3 | 1. MO can edit job details 2. MO can close/delete job postings 3. Affected applicants notified | 3 | Phase 3 - Sprint 4 | 2025-04-20 | 2025-04-30
US020 | Email Notifications | As a user, I want to receive email notifications, so that I stay informed about important updates | Low | 3 | 1. Application status changes trigger emails 2. New job postings notify matching TAs 3. Deadline reminders sent | 3 | Phase 3 - Sprint 4 | 2025-04-15 | 2025-05-20
US021 | Performance Optimization | As a system admin, I want the system to perform optimally, so that users have a smooth experience | Low | 4 | 1. Page load time < 2 seconds 2. Database queries optimized 3. Caching implemented | 5 | Phase 3 - Sprint 4 | 2025-04-15 | 2025-05-20
US022 | User Manual | As a user, I want to access a user manual, so that I can learn how to use the system | Medium | 3 | 1. User manual available in system 2. Help sections for each feature 3. Searchable documentation | 3 | Phase 3 - Sprint 4 | 2025-04-20 | 2025-04-30